## Sheet1
Milestones: | Expected Date of Completion | Actual Date of Completion | Provide reason if milestone was NOT met
Setup Server/ Domain/ SSL | 7/6/21-7/6/21 | 2021-07-22 | Milestone met.
Back-end Development | 7/15/21-7/15/21 |  | Milestone was not met because when trying to associate user uploads to specific user, potential security risk were identified. It turns out that Django is not optimal for serving user-specific database objects on the front end in a secure way. However, I have identified a solution to this problem, but due to time constraints it was not able to be implemented by the deadline. The solution is called nginx.
Front-end Development | 7/18/21-7/18/21 | 2021-07-19 | Milestone met.
Official Launch | 7/19/21-7/19/21 | 2021-07-22 | Milestone met.
Deployment | 7/21/21-7/21/21 | 2021-07-22 | Milestone met.
Tasks: | Expected Date of Completion | Actual Date of Completion | Provide reason if task was NOT met
Design Web Layout | 7/7/21-7/8/21 | 2021-07-08 | Task met.
Analysis | 7/9/21-7/10/21 | 2021-07-09 | Task met.
Testing (Server/SSL) | 7/10/21-7/11/21 | 2021-07-22 | Task met.
Testing(Backend/Frontend) | 7/19/21-7/20/21 | 2021-07-17 | Task met.
Post Deployment Testing | 7/21/21-7/21/21 | 2021-07-22 | Task met.
Post Deployment Changes | 7/22/21-7/22/21 | 2021-07-22 | Task met.
System Testing | 7/22/21-7/22/21 | 2021-07-22 | Task met.
Review Documentation | 7/23/21-7/23/21 | 2021-07-22 | Task met.
Milestone Review | 7/23/21-7/23/21 | 2021-07-23 | Task met.